## Sheet1
HS2/LM Ufton Parish Council and stakeholder meeting re: Ufton pedestrian crossing
2020-12-03
Attendees
Paul Leeman
Ian Crowther - UPC
Sara Louise Lee - WCC
John Tayler - UPC
Alison Willers -SDC
Elisabeth Beloten - Office of Jeremy Wright
Jackie Chapman - UPC
Danielle Pike - The White Hart Pub/Sandwich Shop (DP)
Andy de Bell - BBV (AdB)
John Gunn - LM
Sue Bridges - HS2 (SB)
James Fentiman - LM (JF)
Dhiren Katwa - BBV (DK)
Alpa Patel - LM (AP)
Alessia Rosi - LM (AR)
Apologies
Richard Wright (RW) - Garage owner & landlord of sandwich shop (feedback in AOB)
Name | Notes/question | Answer | Action | Status
Aims and objectives
AP | Explained the aim of the meeting was to go through the preferred solution for the Ufton pedestrian crossing and give the opportunity for attendees to ask any questions
Ufton Pedestrian Crossing - key facts
JF | Provided key information on the characteristics of the crossing
Design of the crossing
JF | Provided key information and details on the proposed design of the crossing
Options considered
JF | Provided details on the previous options considered for the pedestrian crossing, and the reasoning behind current stance
Chosen location
JF | Provided key information and details on the chosen location, the 2020 location
DP | Objecting against chosen location due to its proximity of sandwich shop
Decision matrix
JF | Chosen position allows us to make it work better for people using the crossing and space to congregate
Other locations were too small to get a refuge area without taking additional land
Not much clearance required, no trees needed to be cut - maintenance issues
Better with regards to amount of clearance
This position does not affect the lay-by close to the village hall
Technical considerations
JF | Provided key information and details on the technical considerations for the chosen position for the pedestrian crossing
TBM and Ufton roundabout
AP | The building of the roundabout is not required until the second use of the TBM
Ad | The first time for the TBM will be at some point in June 2021
DK | First delivery is due imminently (weekend of the 5/6 December 2020)
We have done everything possible to mitigate noise and vibration. Between now and the end of March, we are expecting around 60 abnormal loads to be delivered, which will be controlled by Warwickshire police
BBV A425 works update
AdB | Providing details on additional works being carried out in the area by BBV
Phased sequence of works to put the cover section of the tunnel (south portal) under the A425
Moving utilities that are in that area
Move power cables
A haul road under construction allowing 24/7 access to emergency vehicles
Additional works being carried out at the Long Itchington Green Tunnel and south reception portal
Q&A
JT | Question about the roundabout - it will be very useful for us to have a clear idea where the roundabout will go and when it will be re-instated? What's important to us and the community is to not have any surprises. | JG: It has to happen in the middle of next year because it has to be in place for the next tunnel cutting. We can soon get a contract in place and advice regarding the timescales, but currently suggest March/April/May 2021.
IC | Is it correct that the first bore will be in June 2021 and end in September 2021? | Yes, this is approximately correct.
JC | With the tunnel going under the road - does that mean the road will be raised? Daffodils - could we have them planted when the works are over to make up for the ones lost during the works? | AdB: No - the road level stays the same. We will re-instate the road in it's current level. Sounds entirely reasonable - if there is an opportunity for us to store them in a suitable environment or re-plant them then we definitely will.
IC | Who is the main HS2 contact? | Please contact Sue Bridges or Paul Mullins.
| Bus stop lay by would disappear, where will the new one be? | This is not the lay-by for the bus, but for parking in the area.
| Because the crossing has now moved so much closer to the roundabout and Ufton hill, what is the sight line? Where is it marked on the road? | We have looked at this and it's currently under discussion with WCC. There are ways to angle the design and put up warning sings as cars come up the hill, but we do agree that this is something that is slightly different than the position we marked out on site. It will be further examined during the road safety audit.
The proximity to bus stop is concerning with regards to the sight lines. The signs will potentially not be seen and will be too late to warn cars about the pedestrian crossing. Buses - where they are parking and the speed they are coming around the bend. Will the bus hinder cars view on the traffic light and create risk? Measures to slow people down are needed.
JC | Is the lay-by entirely in HA land or is any on private land? Would be helpful to see an exact plan of the crossing and everything related to the crossing. | Not sure - almost certain it all falls within WCC boundary land but need to confirm this. That level of detail will also be shared closer to time.
AW | You mentioned that you considered the village hall lay-by, but that lay-by is not as used as our lay by is. Have you thought about the local businesses in the area? Covid, road issues, we won't have any space for the cars to go. Has this definitely been decided? Our lay-by is used everyday and this will cause massive disruption. Where does this leave us and our business? The lay-by is the area where all the lorries park. What is the timeline? Will construction start around March - April next year? | We have come with this solution and sharing it with you. We will now digest what we have heard tonight and will take this forward. I can't say it's going to change either way, but we will take all circumstances and options into account.
DP | The sight line is a major concern. Signage will not stop people coming at a fast speed. Might it be easier to move the bus stop? The bus will stop there to pick up and drop off people and create a visibility issue. Please consult with the road safety team. However, the pedestrian crossing will make it easier and safer for pedestrians to access the White Hart safely. | Speed surveys have been undertaken - but we agree that we need more consistent surveys over a longer period of time. We can look at sharing information from the road safety surveys. Visibility - my designers wouldn't take something forward that isn't safe. We have liaised with WCC and are aligned with them for this chosen solution.
JT
AOB | RW is the owner of the garage and building where the sandwich shop is located. RW sent his apologies for the meeting however, had submitted feedback to the engagement team as AP explained during the meeting prior. RW reiterated his feedback via email to AP following the meeting on 3/12/20. RW shares the sandwich shop proprietors concerns as it he feels it would render the layby useless and seriously damage their business. He also stated that it will have no contribution whatsoever to traffic calming. The alternative proposal near the Village Hall is much more preferable but would need RW's approval on exact plans regarding obstruction to our workshop entrance from the main road. RW suggested the perfect location is adjacent to the Village Hall entrance/Layby where it does not affect any of the businesses and will serve to slow traffic coming into the village.
RW